REQUEST FOR EXPRESSION OF INTEREST

- REFERENCE NUMBER:

SADC/RPC/TIP/01/2017

REQUEST FOR SERVICES TITLE:

INDIVIDUAL CONSULTANT TO DEVELOP SADC REGIONAL GUIDELINES FOR MONITORING AND REPORTING ON TRAFFICKING IN PERSONS

AUGUST 2017

- Southern African Development Community (SADC) is inviting Individual Consultants to submit their CV and Financial Proposal as an INDIVIDUAL CONSULTANT TO DEVELOP SADC REGIONAL GUIDELINES FOR MONITORING AND REPORTING ON TRAFFICKING IN PERSONS. The Terms of Reference defining the minimum technical requirements for these services are attached as Annex 1 to this Request for Expression of Interest.

- Individual Consultants shall not be eligible for award of this assignment where :

- they are being bankrupt or wound up, are having their affairs administered by the courts, have entered into arrangements with creditors, have suspended business activities, are being subject of proceedings concerning those matters, or are being in any similar situations arising from a similar procedures provided for in the national legislation or regulations of the SADC member states;

- they have been convicted of offences concerning their professional conduct by a judgment which haves the force of res judicata; (i.e. against which no appeal is possible);

- they have been declared guilty of grave professional misconduct proven by any means which SADC Secretariat can justify;

- they have not fulfilled obligations related to the payments of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which they are established or with those countries where the contract is to be performed;

- they have been the subject of a judgment which has the force of res judicata for fraud, corruption, involvement in a criminal organisation or any other illegal activity detrimental to the SADC Secretariat' financial interests; or

- they are being currently subject to an administrative penalty.

- Your Expression of Interest must be presented as per Standard Expression of Interest Forms attached as Annex 2 to this REOI in English language and be accompanied by copies of all the indicated supporting documents. If the supporting documents are not in English, these shall be accompanied by a certified translation into English.

- Your proposal should be addressed and deposited in the tender box located at the Reception of the address below:

The Chairperson

SADC Internal Tender Committee

SADC Secretariat

Private Bag 0095

Gaborone

Botswana

The envelope should be clearly marked “SADC/RPC/TIP/01/2017” – INDIVIDUAL CONSULTANT TO DEVELOP SADC REGIONAL GUIDELINES FOR MONITORING AND REPORTING ON TRAFFICKING IN PERSONS”

- The deadline for submission of your proposal, to the addressed indicated in Paragraph 4 is: 8th September 2017 at 15:00hrs local time

- Proposal submitted by E-mail “are” acceptable and should be sent to mmutasa@sadc.int with copy to imoatshe@sadc.int and jhofnie@sadc.int

The Subject of the email for the electronic submissions should clearly indicate “SADC/RPC/TIP/01/2017” – INDIVIDUAL CONSULTANT TO DEVELOP SADC REGIONAL GUIDELINES FOR MONITORING AND REPORTING ON TRAFFICKING IN PERSONS”

- Your CV will be evaluated against the following criteria.

|  | Criteria | Maximum points allocated |
| --- | --- | --- |
| 1 | Education and Training | 25 |
| 2 | Specific Experience | 50 |
| 3 | General Experience | 25 |
|  | Total | 100 |

- Your proposal should be submitted as per the following instructions, and in accordance with the Terms and Conditions of the Standard Contract attached as Annex 3 to this REOI:

- PRICES: The financial proposal shall be inclusive of all expenses deemed necessary by the Individual Consultant for the performance of the contract.

- EVALUATION AND AWARD OF THE CONTRACT: Expressions of Interest determined to be formal and technical compliant to the requirement will be evaluated by comparison of their prices.

An Expression of Interest is considered compliant to the requirements if: fulfils the formal requirements (see Paragraphs 2,3,4,5,6 and 7 above), has received minimum 80 points at the technical evaluation, and the financial proposal does not exceed the maximum available budget for the contract.

The award will be made to the applicant who obtained the highest technical score and submitted administrative and technical compliant Expression of Interest.

- VALIDITY OF THE EXPRESSION OF INTEREST: Your Expression of Interest should be valid for a period of 90 days from the date for deadline for submission indicated in Paragraph 5 above.

- The assignment is expected to commence within One (1) week from the signature of the contract.

- Additional request for information and clarifications can be requested, no later than 5 working days prior to deadline indicated in the paragraph 5 above, from:

Procuring entity: SADC Secretariat

Contact person: Mr Gift Mike Gwaza

Telephone: +267 3951863

Fax +267 3181070

E-mail: ggwaza@sadc.int

ANNEXES:

ANNEX 1: Terms of Reference

ANNEX 2: Expression of Interest Forms

ANNEX 3: Standard Contract for Individual Consultants

Sincerely,

Gift Mike Gwaza MCIPS

Acting Head - Procurement Unit

ANNEX 1:

Terms of Reference

SPECIFIC TERMS OF REFERENCE

Individual consultancy for Development of SADC Regional Guidelines for Monitoring and Reporting on Trafficking in Persons

- BACKGROUND TO THE SADC REGIONAL POLITICAL COOPERATION (RPC) PROGRAMME

The European Union (EU) funded “Support to SADC Regional Political Cooperation (RPC)” Programme is designed to strengthen the capacity of the SADC Secretariat and more specifically the Organ on Politics, Defence and Security Cooperation (“the Organ”) in implementing its mandate to effect regional integration in the political and security sectors.

Overall Objective:

To promote peace and security, as a basis for economic growth and poverty reduction in the SADC Region

Purpose:

To strengthen the capacity of SADC to perform its mandate in the area of politics, governance, peace and security

Result Areas:

The Regional Political Cooperation (RPC) Programme, which commenced in April 2013, has four (4) key result areas including Countering Trafficking in Persons.

This assignment will be restricted to KRA 4 on Countering Trafficking in Persons. The main activities (in brief) that are being implemented under this Result Area are as follows:

- Activity 1: 	Strengthen SADC Secretariat capacity to effectively facilitate, monitor and evaluate the implementation of the Regional Strategic Plan of Action on trafficking in persons

The implementation of the programme’s activities is being carried out by the SADC Secretariat Gender Unit in close collaboration with the Police and Public Security Sectors in the Organ Directorate. The 10 Year SADC Strategic Plan of Action on Combating Trafficking in Persons, especially Women and Children (2009-2019) is the guiding document informing the implementation of the programme activities on trafficking in persons.

Activity 2: 	Develop and strengthen inter-State cooperation and capacity in combating trafficking in persons

This activity aims to establish and strengthen channels of communication between Member States’ law enforcement, immigration, border control agencies and other relevant sectors for the purpose of sharing intelligence, information and trends on trafficking in persons. This has resulted in the development of a regional database on trafficking in persons, a comprehensive resource for data on trafficking in persons in the SADC region as well as relevant national legislation on the crime.

Activity 3: 	Strengthen the capacity of stakeholders in the SADC region to effectively combat trafficking in persons, especially women and children

The RPC programme is in the process of developing a training curriculum on trafficking in persons, which will be used both for the training of trainers and for training of law enforcement personnel, customs and immigration officials, social workers, prosecutors and judges, and relevant stakeholders in the investigation, prevention and prosecution of trafficking in persons, and on the protection of the trafficked survivors, especially women and children.

- DESCRIPTION OF THE ASSIGNMENT

Research on trafficking in persons in the SADC region acknowledges that the crime is a public security concern in the region, and its impacts “are far-reaching, affecting individuals, communities and the wider region thereby depreciating the socio-economic status of [its] citizens”. The crime of trafficking in persons also impacts negatively on the region’s peace and security agenda and, ultimately, SADC’s efforts to achieve regional integration.

SADC Member States’ commitment to countering the crime was evidenced by the adoption of the 10 Year SADC Strategic Plan of Action on Combating Trafficking in Persons, especially Women and Children (2009-2019) in 2009. The Strategic Plan of Action identified legislation and policy measures, training for skills strengthening and capacity building, prevention and public awareness, victim support and witness protection, coordination and regional cooperation, research and information sharing, monitoring and evaluation, and resource mobilisation as the eight (8) strategic priorities for action in the drive to combat this heinous crime in the region.

In 2016, the Strategic Plan of Action was subjected to a mid-term review in order to inform the priorities for the subsequent five years of the Plan. This review was also guided by the SADC Policy for Strategy Development, Planning, Monitoring and Evaluation, which emphasises that the “evaluation of protocols and other core policies will provide insights mainly on the relevance, effectiveness, impact and sustainability of SADC regional policy in the various sectors of intervention.”

This recognises the important of monitoring and reporting on the crime of trafficking in persons in the SADC region, which is also identified as key to responding to the crime at the global level. For example, the Conference of the Parties to the United Nations Convention against Transnational Organised Crime’s Working Group on Trafficking in Persons, at its meeting in April 2009 in Vienna, Austria, recommended that States parties to the Convention should “contribute national data to a database administered by the Secretariat to measure the response to trafficking in persons”. Such a database should then be used for data collection, research and analysis on trafficking in persons. It is, therefore, in view of this that the SADC Secretariat plans to develop Guidelines for Monitoring and Reporting on Trafficking in Persons. This is also in response to a recommendation for SADC Member States to “establish uniform planning, monitoring, evaluation and reporting guidelines and indicators at national and regional levels for monitoring, evaluation and reporting on trafficking in persons.”

Global objective:

The assignment seeks to strengthen the SADC region’s response to the crime of trafficking in persons, in particular in monitoring, evaluation and reporting on trafficking in persons.

It responds to the strategic priority area on Monitoring, Evaluation and Reporting as outlined in the overarching policy framework on trafficking in persons in the SADC region – the Revised SADC Strategic Plan of Action on Combating Trafficking in Persons (2016-2019).

Purpose and specific objectives

The main purpose of the assignment is to develop the SADC Guidelines for Monitoring and Reporting on Trafficking in Persons, clearly articulating monitoring and reporting responsibilities, sources of evidence, and frequency of reporting on trafficking in persons.

Specifically, the assignment will seek to develop:

- guidelines for monitoring and reporting on trafficking in persons, aligned to relevant global, regional and national frameworks;

- a list of indicators and accompanying questions to guide data collection, analysis and reporting on trafficking in persons; and

- a data collection tool to use for the purposes of data gathering and reporting on trafficking in persons in the SADC region.

The consultancy will involve:

- Developing the draft SADC Guidelines on Monitoring and Reporting on Trafficking in Persons, in consultation with relevant sectors in SADC Secretariat, Member States government departments, and relevant stakeholders in the region. The development process should also learn from other Guidelines developed in the region and beyond;

- Facilitating and rapporteuring a regional workshop, convened by SADC Secretariat, to validate the draft SADC Guidelines on Monitoring and Reporting on Trafficking in Persons, and submitting a report of the validation process;

- Finalising and submitting the draft SADC Guidelines on Monitoring and Reporting on Trafficking in Persons based on the inputs from the regional workshop convened to validate the guidelines.

Requested services

This request is for monitoring, evaluation and reporting expert to develop the draft SADC Guidelines on Monitoring and Reporting on Trafficking in Persons as outlined under the Description of the Assignment above.

Key deliverables

The key deliverables of this consultancy will be:

- A final detailed inception report outlining the consultant’s understanding of the assignment and the approach to be employed. The inception report will be discussed prior to the commencement of the assignment;

- DRAFT SADC Guidelines on Monitoring and Reporting on Trafficking in Persons, which will be subjected to a validation process in the form of a regional workshop convened by SADC Secretariat. The Consultant will also be responsible for facilitating and rapporteuring this regional validation workshop;

- FINAL SADC Guidelines on Monitoring and Reporting on Trafficking in Persons detailing, among others, the monitoring and reporting responsibilities, sources of evidence, indicators to track, and frequency of reporting on trafficking in persons; and

- Final detailed report of the regional workshop to validate the SADC Guidelines on Monitoring and Reporting on Trafficking in Persons.

- EXPERT’S PROFILE or EXPERTISE REQUIRED

The assignment is for a consultant with expertise in the areas of strategic planning; monitoring, evaluation and reporting; and research. The consultant should possess an understanding of transnational organised crime particularly on trafficking in person, smuggling of migration and irregular migration.

The following are the requirements for this consultancy:

Minimum requirements:

- Postgraduate degree in Development Studies, Gender Studies, or any related Social Science discipline; and

- At least ten years’ progressive professional experience in reporting, monitoring and evaluation; knowledge management; research and documentation; or any social science discipline

Specific/other requirements:

- Traceable experience in monitoring, evaluation and reporting; and social research;

- High level qualitative and/or quantitative research, in particular data collection and analysis skills;

- Excellent report writing and workshop facilitation skills;

- MS Office computer package proficiency;

- Be a resident of the SADC region with experience working in the region; and

- Fluency in spoken and written English. Knowledge of Portuguese and French will be an added advantage.

Gender Mainstreaming

The SADC Secretariat is an equal opportunities employer, and particularly encourages applications from qualifying female candidates.

- SELECTION CRITERIA

Eligible consultants are requested to submit, in their application packages, sample(s) of their previous work related to monitoring, evaluation and reporting, undertaken either in their individual capacities or as members of a team. The bid evaluation criteria will be as follows:

| Category | Maximum Score |
| --- | --- |
| Education and Training | 25 |
| Specific Experience – including samples | 50 |
| General Experience | 25 |
| Total | 100 |

- DURATION

This assignment will run for 30 working days spread over a period not exceeding two calendar months, inclusive of the inception meeting, development of the SADC Guidelines on Monitoring and Reporting on Trafficking in Persons, validation workshop and finalisation and submission of the key outputs.

| Deliverable | Timeframe (# of days) |
| --- | --- |
| Final inception report detailing the methodology/ conceptual framework to be employed. This will be finalised based on inputs from the inception meeting to be held at SADC Secretariat | 5 (from day of contract signature) |
| Draft SADC Guidelines on Monitoring and Reporting on Trafficking in Persons | 12 |
| Documentation for Regional Validation Workshop (preparations for regional workshop) | 3 |
| Workshop presentations, facilitation and rapporteuring (workshop to be convened by SADC Secretariat) | 5 |
| Final: - SADC Guidelines on Monitoring and Reporting on Trafficking in Persons - Detailed Regional Validation Workshop Report | 5 |
| Total | 30 |

- BUDGET/ REMUNERATION

The budget ceiling for this assignment is $10,500. The application should include a detailed budget.

The payment schedule will be as follows:

20% of the contract value upon submission of Final Inception Report, detailing the methodology or conceptual framework to be employed, acceptable to the Procuring Entity;

30% of the contract value upon submission of the draft SADC Guidelines on Monitoring and Reporting on Trafficking in Persons, acceptable to the Procuring Entity; and

50% of the contract value upon submission of final SADC Guidelines on Monitoring and Reporting on Trafficking in Persons, and the detailed Regional Validation Workshop Report.

- REPORTING

The Consultant shall report to, and perform the assigned tasks under the guidance and direct supervision of the Programmer Officer: Research, Information and Documentation at the SADC Secretariat who will facilitate the team’s contacts with key stakeholders and facilitate access to relevant documents and information.

The Research, Information and Documentation programme officer will, in the implementation of this activity, be in constant consultation with the staff of the SADC Secretariat, in particular the Directorate of Gender, Social and Human Development; Directorate of the Organ on Politics, Defence and Security Affairs; and the Directorate for Policy, Planning and Resource Mobilisation.

ANNEX 2: Expression of Interest Forms

A.	COVER LETTER FOR THE EXPESSION OF INTEREST FOR THE PROJECT	17

B.	CURRICULUM VITAE	19

C.	FINANCIAL PROPOSAL	24

# A.	COVER LETTER FOR THE EXPESSION OF INTEREST FOR THE PROJECT

[insert name and reference number]

[Location, Date]

To:	[Name and address of Procuring Entity]

Dear Sirs:

I, the undersigned, offer to provide the consulting services for [insert title of assignment] in accordance with your Request for Expression of Interests number [insert the number], dated [insert date] and my Financial Proposal for the sum of [Insert amount(s) in words and figures1].  This amount inclusive of all expenses deemed necessary for the performance of the contract in accordance with the Terms of Reference requirements, and [“does” or “does not” delete as applicable] include any of the following taxes in Procuring Entity’s country: value added tax and social charges or/and income taxes on fees and benefits.

I hereby declare that all the information and statements made in CV are true and accept that any misinterpretation contained in it may lead to my disqualification.

I take note that under the provisions of the SADC Procurement Policy applicable to this Request For Expression of Interest, a contract cannot be awarded to applicants who are in any of the following situations:

a) they are being bankrupt or wound up, are having their affairs administered by the courts, have entered into arrangements with creditors, have suspended business activities, are being subject of proceedings concerning those matters, or are being in any similar situations arising from a similar procedures provided for in the national legislation or regulations of the SADC member states;

b) they have been convicted of offences concerning their professional conduct by a judgment which haves the force of res judicata; (i.e. against which no appeal is possible);

c) they have been declared guilty of grave professional misconduct proven by any means which SADC Secretariat can justify;

d) they have not fulfilled obligations related to the payments of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which they are established or with those countries where the contract is to be performed;

e) they have been the subject of a judgment which has the force of res judicata for fraud, corruption, involvement in a criminal organisation or any other illegal activity detrimental to the SADC Secretariat' financial interests; or

f) they are being currently subject to an administrative penalty.

I confirm that I am not in any of the situations described above, and I hereby declare that at any point in time, at the SADC Secretariat request, I will provide certified copies of documents to prove that I do not follow in any of the situation described above.

I am aware that the penalties set out in the Procurement Policy may be applied in the case of a false declaration, should the contract be awarded to me.

My proposal is binding upon me for the period indicated in the Paragraph 9(iii) of the Request for Expression of Interest.

- I undertake, if our Proposal is accepted, to initiate the consulting services related to the assignment not later than the date indicated in Paragraph 10 of the Request for Expression of Interest, and to be available for the entire duration the contract as specified in the Terms of Reference.

I understand you are not bound to accept any Proposal you receive.

Yours sincerely,

Signature [In full and initials]:

Name and Title of Signatory:

- B.	CURRICULUM VITAE

[insert the full name]

| 1. Family name: | [insert the name] |
| --- | --- |
| 2. First names: | [insert the names in full] |
| 3. Date of birth: | [insert the date] |
| 4. Nationality: | [insert the country or countries of citizenship] |
| 5. Civil status: | [insert: married/ divorced/single/ widower] |
| 6. Purchase Order details: | Address:[insert the physical address] |
|  | Phone :[insert the phone and mobile no.] |
|  | E-mail: [insert the email] |
| 8. Education: |  |
| Institution: [Date from – Date to] | Degree(s) or Diploma(s) obtained: |
| [indicate the month and the year] | [insert the name of the diploma and the specialty/major] |
| [indicate the month and the year] | [insert the name of the diploma and the specialty/major] |

7.	Language skills: (Indicate competence on a scale of 1 to 5) (1 – excellent; 5 – basic)

| Language | Reading | Speaking | Writing |
| --- | --- | --- | --- |
| [insert the language] | [insert the no.] | [insert the no.] | [insert the no.] |
| [insert the no.] | [insert the no.] | [insert the no.] | [insert the no.] |
| [insert the no.] | [insert the no.] | [insert the no.] | [insert the no.] |

| 8. Membership of professional bodies: | [indicate the name of the professional body] |
| --- | --- |
| 9. Other skills: | [insert the skills] |
| 10. Present position: | [insert the name] |
| 11. Years of experience: | [insert the no] |
| 12. Key qualifications: (Relevant to the assignment) [insert the key qualifications] |  |

13.	Specific experience in the region:

| Country | Date from - Date to |
| --- | --- |
| [insert the country] | [indicate the month and the year] |
| ................ | ...................... |
| [insert the country] | [indicate the month and the year] |

- Professional experience:

| Date from – Date to | Location of the assignment | Company& reference person (name & contact details) | Position | Description |
| --- | --- | --- | --- | --- |
| [indicate the month and the year] | [indicate the country and the city] | Name of the Company: Address of the company: Phone: Fax: Email: Name and title of the reference person from the company: | [indicate the exact name and title and if it was a short term or a long term position] | Name of the Purchase Order: Beneficiary of the Purchase Order: Brief description of the Purchase Order: Responsibilities: |
| [indicate the month and the year] | [indicate the country and the city] | Name of the Company: Address of the company: Phone: Fax: Email: Name and title of the reference person from the company: | [indicate the exact name and title and if it was a short term or a long term position] | Name of the Purchase Order: Beneficiary of the Purchase Order: Brief description of the Purchase Order: Responsibilities: |
| [indicate the month and the year] | [indicate the country and the city] | Name of the Company: Address of the company: Phone: Fax: Email: Name and title of the reference person from the company: | [indicate the exact name and title and if it was a short term or a long term position] | Name of the Purchase Order: Beneficiary of the Purchase Order: Brief description of the Purchase Order: Responsibilities: |
| ................ | …………….. | ……………………. | …………… | ………………………………………………………………………….. |
| [indicate the month and the year] | [indicate the country and the city] | Name of the Company: Address of the company: Phone: Fax: Email: Name and title of the reference person from the company: | [indicate the exact name and title and if it was a short term or a long term position] | Name of the Purchase Order: Beneficiary of the Purchase Order: Brief description of the Purchase Order: Responsibilities: |

- Other relevant information: (e.g. Publications)

[insert the details]

- Statement:

I, the undersigned, certify that to the best of my knowledge and belief, this CV correctly describes myself, my qualifications, and my experience. I understand that any wilful misstatement described herein may lead to my disqualification or dismissal, if engaged.

I hereby declare that at any point in time, at the SADC Secretariat request, I will provide certified copies of all documents to prove that I have the qualifications and the professional experience and indicated at points 8 and 14 above, documents which are attached to this CV as photocopies.

By signing this statement, I also authorized the SADC Secretariat to contact my previous or current employers indicated at point 14 above, to obtain directly reference about my professional conduct and achievements.

|  | Date: | 28 July 2026 |
| --- | --- | --- |

ATTACHMENTS: 	1) Proof of qualifications indicated at point 8
			2) Proof of working experience indicated at point 14

# C.	FINANCIAL PROPOSAL

[insert name and reference number]

| N° | Description |  | Unit | No. of Units | Unit Cost (in US$) | Total (in US$) |
| --- | --- | --- | --- | --- | --- | --- |
| Fees |  |  | Day |  |  |  |
| Reimbursable expenses, out of which |  |  | Total |  |  |  |
| 1 | Per diem allowances |  | Day |  |  |  |
| 2 | Flights |  | Trip |  |  |  |
| 3 | Miscellaneous travel expenses |  | Trip |  |  |  |
| 4 | Insurances cost, out of which: |  | Lump sum |  |  |  |
|  | i) | Life insurance (including repatriation) | Lump sum |  |  |  |
|  | ii) | Heath insurance | Lump sum |  |  |  |
|  | iii) | Third party liability insurance | Lump sum |  |  |  |
|  | iv) | Professional liability insurance | Lump sum |  |  |  |
| 5 | Drafting, reproduction of reports |  | Lump sum |  |  |  |
| 6 | Office rent |  | Per month |  |  |  |
| 7 | Others4 |  | TBD |  |  |  |
| TOTAL FINANCIAL OFFER (Fees + Reimbursable expenses) |  |  |  |  |  |  |

Signature [In full and initials]:

Name and Title of Signatory:

ANNEX 3: STANDARD CONTRACT FOR INDIVIDUAL CONSULTANT

STANDARD TERMS OF CONTRACT (Individual Consultant)

Contract Name [insert the name]

Contract Number [insert the number]

THIS Contract (“Contract”) is made on [day] day of the month of [month], [year], between, on the one hand,

[name of Procuring Entity] (hereinafter called the “Procuring Entity”) with the registered business in [insert the name address, phone, fax and email of the procurement entity]

and, on the other hand,

[insert the full name of the individual] (hereinafter called the “Individual Consultant”), with the residence in [insert the Individual Consultant’ address, phone, fax, email], citizen of [insert the Individual Consultant’s citizenship] owner of the ID/Passport Number [insert the number] issued on [insert the date] by [insert the name of the issuance authority],

WHEREAS, the Procuring Entity wishes to have the Individual Consultant perform the services hereinafter referred to, and WHEREAS, the Individual Consultant is willing to perform these services,

NOW THEREFORE THE PARTIES hereby agree as follows:

- Definitions

For the purpose of this contract the following definitions shall be used:

  - Procuring Entity means the legally entity, namely [insert the name] who purchase the Services described in Annex 1 to this contract.

  - Contract means the agreement covered by these Terms including the Annexes and documents incorporated and/or referred to therein, and attachments thereto.

  - Contract value means the total price of the Financial Proposal included in the Individual Consultant’s Expression of Interests dated [insert the date] for the project [insert the name] and reflected as such in the Annex 2 of this contract.

  - Individual Consultant means the individual to whom the Procuring Entity has awarded this contract following the Request for Expression of Interest [insert the number] for the project [insert the name].

  - Services means the Services to be performed by the Individual Consultant as more particularly described in Annex 1; for the avoidance of doubt the Services to be performed include all obligations referred to in this Contract (as defined above).

- The Services

The Individual Consultant will undertake the performance of the Services in accordance with the provisions of the Annex 1 of this Contract and shall in the performance of the Services exercise all the reasonable skill, care and diligence to be expected of an Individual Consultant carrying out such services.

- Payment

  - The Individual Consultant shall be paid for the Services at the rates and upon the terms set out in Annex 2.

  - Payment shall be made to the Individual Consultant in US $ unless otherwise provided by this contract and where applicable VAT shall be payable on such sums at the applicable rate. The Individual Consultant must, in all cases, provide their VAT registration number on all invoices.

  - Unless otherwise provided in this Contract, invoices shall be delivered to and made out to Procuring Entity and shall be paid within 30 days of receipt by Project Director, subject to the Individual Consultant having complied with its obligations hereunder in full as stated in the Annex II to this Contract. Procuring Entity reserves the right to delay and/or withhold, fully or partially, payments that have not been supported by full and appropriate supporting evidence that the services provided were delivered and accepted by the Procuring Entity.

- Status of the Individual Consultant

  - For the duration of the Contract the Individual Consultant will have a status similar to the Procuring Entity’s employees with regards to their legal obligations, privileges and indemnities in the Procuring Entity’s country.

  - The Procuring Entity will be responsible for ensuring all visas, work permits and other legal requirements to enable The Individual Consultant and live and work in the countries of the assignment as per the duties under the contract.

  - The Individual Consultant shall be responsible for paying any tax and social security contributions in its country of residence, for any activity deriving from this contract. Such costs shall be assumed included in the Individual Consultant’s fees.

  - The Procuring Entity shall be responsible for paying any taxes resulting from the activities performed under this contract imposed to the Individual in the country(ies) of the assignment with the exception of the ones set out in paragraph 5.3 above.

- Supervision of the Services

The Individual Consultant undertakes to deliver the Services in compliance with a system of quality assurance acceptable to Procuring Entity which shall include any steps to comply with the standards operated by Procuring Entity. The Individual Consultant shall be informed of the specific requirements in relation to this, and at the request of Procuring Entity shall afford such access to its information, records and other materials during normal office working hours as Procuring Entity may require in order to confirm that the work in progress is in accordance with these quality procedures.

- Compliance with this contract

Procuring Entity will be entitled to seek confirmation from the Individual Consultant, at any time during the delivery of this contract, and for a period of 1 year after its completion, that the Individual Consultant has complied with the terms of this contract. Procuring Entity may also request the provision of reasonable documentary evidence to support this.  As stated in article 2.3 of this Contract, Procuring Entity may delay or withhold payments in the event of non-compliance.

- Assignment and Subcontracting

  - The Individual Consultant shall under no circumstances sub-contract, sublet, assign or transfer the Contract or any part share or interest in it.  Where the Individual Consultant considers it necessary to use the services of a third party the Individual Consultant shall inform the Procuring Entity the Project Director in writing, and only once written approval is provided can the Individual Consultant proceed to use a third party.

  - When the Project Director agrees that the activities under the contract can be performed by third party, the third party involved in the delivery of services in this contract, will be under the direct control of Individual Consultant. Procuring Entity will not be responsible for the third party performance of duties or Services assigned to third party, and neither for ensuring conditions of employment are met nor for any other employment obligations relating to that person including, but not restricted to, taxation and insurance including professional indemnity insurance, employer’s liability insurance and public liability insurance.

- Breach of the Terms

In the event of a breach of any Terms of the Contract the party not in breach may serve a notice on the party in breach requiring the breach to be remedied within a period specified in the notice, not normally being longer than 30 days.  If the breach has not been remedied before the expiry of the specified period, the party not in breach may then terminate the Contract in writing and may take appropriate steps to remedy the breach.

- Liability of the Individual Consultant

  - Procuring Entity will be relying on the Individual Consultant’s skills, expertise and experience in relation to the performance of the Services in accordance with this contract and also upon the accuracy of all representations and statements made and the advice given by the Individual Consultant in connection with the provision of the Services.

  - In view of the reliance by Procuring Entity set out in 10.1 above the Individual Consultant agrees at its own expense to indemnify, protect and defend Procuring Entity, its agents and employees, from and against all actions, claims, losses or damages arising out of the Individual Consultant's performance of this contract provided that:

- the Individual Consultant is notified of such actions, claims, losses or damages not later than 30 days after Procuring Entity becomes aware of them;

- the ceiling on the Individual Consultant's liability to Procuring Entity shall be limited to an amount equal to the contract value, and such ceiling shall not apply to any losses or damages caused to third parties by the Individual Consultant or by the Individual Consultant's willful misconduct; and

- the Individual Consultant's liability shall be limited to actions, claims, losses or damages directly caused by such failure to perform its obligations under the contract and shall not include liability arising from unforeseeable occurrences incidental or indirectly consequential to such failure.

  - At its own expense, the Individual Consultant shall, upon request of Procuring Entity, remedy any defect in the performance of the services in the event of the Individual Consultant's failure to perform its obligations under the contract.

  - The Individual Consultant shall have no liability whatsoever for actions, claims, losses or damages occasioned by Procuring Entity omitting to act on any recommendation, or overriding any act, decision or recommendation, of the Individual Consultant, or requiring the Individual Consultant to implement a decision or recommendation with which the Individual Consultant disagrees or on which it expresses a serious reservation.

- Insurance

  - The Individual Consultant must ensure that full and appropriate professional indemnity insurance, third party liability insurance, life/travel and health insurance is in place for all Services provided. The Individual Consultant is obliged to provide full copies of such insurance within 45 days from the signature of this Contract.

  - The cost of such insurances will be covered from reimbursable expenses of the contract.

  - Where national requirements or practices provide for different regulations/practices concerning insurance, the Individual Consultant may provide written confirmation of all insurances held and a signed declaration that these are in line with regulations/practices in their country of operation.  Only if such confirmation has been provided, and written confirmation of its acceptance provided to the Individual Consultant by Procuring Entity, will this remove the obligation to meet the requirements of clause 11.1 of this Contract in full.

  - All insurances effected by the Individual Consultant shall be effected with an insurer of good repute and the Individual Consultant agrees to maintain such insurances for a period of 1 year from the completion of the Services under this Contract so long as such insurance continues to be available upon reasonable terms at reasonable commercial rates failing which Procuring Entity shall be entitled to take out insurance itself to cover any potential liability to its own Procuring Entity in relation to the performance of the Services under this contract. The cost of such insurance shall be a debt immediately due from the Individual Consultant.

  - The provisions of this clause shall remain in full force and effect notwithstanding the completion of the performance of the Services hereunder and the satisfaction of all other provisions of this contract.

- Copyright

  - Unless otherwise specified in the Contract, the title of the copyright and any other intellectual property rights arising out of the performance of this Contract shall be vested in Procuring Entity which shall have the unfettered right to assign and grant sub-licences in respect of the same. Except as permitted by the Terms of this Contract, the said materials shall not be reproduced or disseminated without proper consultation with, and written permission from, the Procuring Entity. This provision shall apply to the title to rights arising from the performance under this contract but shall not apply to the internal systems or rights in relation to the Individual Consultant’s own systems not created specifically for this purpose and where the same are an important part of the Services the Individual Consultant shall grant a free and irrevocable licence to Procuring Entity and its assigns for the use of the same in that connection.

  - The Individual Consultant warrants that it is free of any duties or obligations to third parties which may conflict with this contract and, without prejudice to the generality of Term 9 above, agrees to indemnify Procuring Entity against any and all actions, costs damages, direct, indirect or consequential, and other expenses of any nature whatsoever which Procuring Entity may incur or suffer as a result of the breach by the Individual Consultant of this warranty.

- Non Disclosure & Confidentiality

  - The Individual Consultant will treat as confidential all information and results obtained in discharging the Services under this Contract and will not disclose by any means whatsoever such results or material to any third party without the prior written consent of the Procuring Entity and will only use such information for the purposes of this Contract. In addition the Individual Consultant shall not make any communication to the press or any broadcast (including, but not limited to, inclusion of information on a website) about the Services without the prior agreement in writing of the Project Director.

  - If the Individual Consultant violates clause 13.1, then it will automatically and legally be held to pay the amount estimated as the minimum reasonable damages resulting from a breach of confidentiality. This is without prejudice to the right of Procuring Entity to demonstrate that a higher amount of loss has or may be incurred as a result of liabilities held by Procuring Entity in relation to the Procuring Entity.

- Suspension or Termination

  - In response to any factors outwith the control of Procuring Entity and/or to breaches of contract, Procuring Entity may at any time, by giving 30 days notice in writing, terminate in whole or in part the Individual Consultant’s appointment hereunder but in the event of Procuring Entity doing so then the Individual Consultant shall be entitled to payment as set out in sub-clause 14.4 below.

  - In response to any factors outwith the control of Procuring Entity and/or to breaches of contract, Procuring Entity may at any time, by giving 30 days notice in writing, forthwith require the Individual Consultant to suspend the performance of the Services and in such event the Individual Consultant shall be entitled to payment pursuant to sub-clause 13.4 below and provided that if such suspension continues for a period in excess of twelve months then either party may terminate this appointment forthwith by written notice to the other.

  - The Individual Consultant may also terminate the contract unilaterally, without providing any reasons for such decision, if she/he gives a 30 days prior written notice to the Project Director.

  - In the event of early termination of the Contract under sub-clauses 14.1, 14.2 and 14.3 of this clause then the Individual Consultant shall be entitled to a fair and reasonable proportion of the fees payable for that part of the Services carried out up to the date of such termination or suspension but this shall not include any loss of profit or contracts or any other expenses, losses or claims arising out of such termination or suspension or consequential thereupon.

- No Waiver

No forbearance shown or granted to the Individual Consultant unless in writing by an authorised officer of Procuring Entity shall in any way affect or prejudice the rights of Procuring Entity or be taken as a waiver of any of these Terms.

- Variations

Any variation to these terms or the provisions of the Annexes shall be subject to  written Addendum and be signed by duly authorised signatories on behalf of the Individual Consultant and Procuring Entity respectively.

- Jurisdiction

This contract shall be governed by and shall be construed in accordance with Botswana law and each party agrees to submit to the exclusive jurisdiction of the Botswana courts as regards any claim or matter arising under this contract.

The following Annexes are integral part of this Contract:

Annex 1: Terms of Reference

Annex 2: Payment Schedule and Requirements

Signed today [insert the date] in four (4) originals in English language by:

| For the Procuring Entity | Signature |  | For the Individual Consultant | Signature |
| --- | --- | --- | --- | --- |
| Name: [insert full name] |  |  | Name: [insert full name] |  |
| Title:[insert the title] |  |  | Title:[insert the title] |  |
| Palace: [insert the city and country] |  |  | Palace: [insert the city and country] |  |
| Date: [insert the date] |  |  | Date: [insert the date] |  |

Annex 1: Terms of Reference

[insert the Terms of Reference]

Annex 2: Payment Schedule and Requirements

  - For Services rendered pursuant to Annex 1, the Procuring Entity shall pay the Individual Consultant an amount not to exceed a ceiling of US Dollars [insert ceiling amount], which shall be considered the contract value. This amount has been established based on the understanding that it includes all of the Consultant’s costs and profits as well as any tax obligation that may be imposed on the Individual Consultant in its country of residence.

  - The breakdown of prices is: [fill in the table as per the Individual Consultant’ Financial Proposal presented in the Expression of Interest]

| N° | Description |  | Unit | No. of Units | Unit Cost (in US$) | Total (in US$) |
| --- | --- | --- | --- | --- | --- | --- |
| Fees |  |  | Day |  |  |  |
| Reimbursable expenses, out of which |  |  | Total |  |  |  |
| 1 | Per diem allowances |  | Day |  |  |  |
| 2 | Flights |  | Trip |  |  |  |
| 3 | Miscellaneous travel expenses |  | Trip |  |  |  |
| 4 | Insurances cost, out of which: |  | Lump sum |  |  |  |
|  | i) | Life insurance (including repatriation) | Lump sum |  |  |  |
|  | ii) | Heath insurance | Lump sum |  |  |  |
|  | iii) | Third party liability insurance | Lump sum |  |  |  |
|  | iv) | Professional liability insurance | Lump sum |  |  |  |
| 5 | Drafting, reproduction of reports |  | Lump sum |  |  |  |
| 6 | Office rent |  | Per month |  |  |  |
| 7 | Others4 |  | TBD |  |  |  |
| TOTAL FINANCIAL OFFER (Fees + Reimbursable expenses) |  |  |  |  |  |  |

3. The payment shall be made in accordance with the following schedule: [delete as appropriate]

“	Option 1: - lump sum contracts

[insert amount (which shall me maximum 20% of the contract value) and currency] upon the Procuring Entity's receipt of a copy of this Contract signed by the Individual Consultant ;

[insert amount and currency] upon the Procuring Entity’s receipt of the [insert the name and the description of the deliverable], acceptable to the Procuring Entity;

[insert amount and currency] upon the Procuring Entity’s receipt of the [insert the name and the description of the deliverable], acceptable to the Procuring Entity; and

[insert amount (minimum 10% and maximum 30% of the contract value) and currency] upon the Purchaser’s receipt of the final report, acceptable to the Procuring Entity.

[insert amount and currency] Total

Option 2: - time based contracts

The payments made under the Contract consist of the Individual Consultant's remuneration as defined in sub-paragraph a) below and of the reimbursable expenditures as defined in sub-paragraph b) below.

a)	Remuneration

The Procuring Entity shall pay the Individual Consultant for Services rendered at the rate(s) per day spent, subject to a maximum of eight hours per day in accordance with the rates agreed and specified in paragraph 2 above.

The proof of Individual Consultant’s performance of services shall be the monthly timesheet signed by expert and approved by the Procuring Entity.

b)	Reimbursables

The Procuring Entity shall pay the Individual Consultant for reimbursable expenses specified in the paragraph 2 above against the submission of the original documents to prove the incurrence of such expense.

Perdiem shall be paid for every night spent by the Individual Consultant, for the purpose of the implementation of this contract, in a location outside the Country of her/his residence. The proof of incurrence of such expense shall be the timesheet approved by the Procuring Entity.“

4. Payment Conditions: Payment shall be made in US Dollars not later than 30 days following submission by the Individual Consultant of original invoice, in duplicate, accompanied by the requested supporting documents, to the Procuring Entity. All payments under the contract shall be made by bank transfer into the bank account indicated by the Individual Consultant in her/his invoices.

SADC. 2016. Trafficking in Persons in the SADC Region: a Baseline Report. Gaborone, SADC Secretariat. Available at http://www.sadc.int/files/3514/7505/0085/SADC_Baseline_Report_Low_Resolution.pdf, accessed on 09 June 2017

See http://www.sadc.int/files/8713/6621/3373/SPME_Policy_English_Final.pdf

Report on the meeting of the Working Group on Trafficking in Persons held in Vienna on 14 and 15 April 2009. Available at https://www.unodc.org/documents/treaties/organized_crime/Final_report_English_TIP.pdf (p.5)

Trafficking in Persons in the SADC Region Policy Brief, August 2016. Available at http://www.sadc.int/files/8414/7505/0081/SADC_TIP_Policy_Brief_-_English_FINAL.pdf

Amounts must coincide with the ones indicated under Total Cost of Financial proposal in Form FIN-2.

The proof of stated qualifications shall be in the form of the copies of the degrees and diploma obtained, while for the professional experience the proof shall be either acknowledgement letters from the previous employers or copies of the Purchase Order signed with them.

Delete items that are not applicable or add other items as the case may be.

Indicate unit cost..

Indicate route of each flight, and if the trip is one- or two-ways

Provide clear description of what is their exact nature

Delete items that are not applicable or add other items as the case may be.

Indicate route of each flight, and if the trip is one- or two-ways.

Indicate unit cost.

Provide clear description of what is their exact nature